## document list-07
PROJECT NAME : Engineering, Procurement, Construction of 132/33 kV GIS Substation of ABADAN OIL REFINERY and connecting to the Power Grid
| DOCUMENT NO :6154-MN-LST-0001 |  | PROJECT NO :96-73-6154
| DOCUMENT TITLE :MASTER DOCUMENT LIST |  | REV : 07
PAGE :1-11
| Document Number | Document Title | Doc. Class | PHASE | STAGE
132/ 33 KV NEW SUBSTATION OF ABADAN OIL REFINERY
SAFETY AND FIRE FIGHTING :
289 | 6154-SA-DIG-0321 | F&GSYSTEM BLOCK DIAGRAM | A | BASIC | ENGINEERING | 1
290 | 6154-SA-MTO-0322 | MTO FOR F&G SYSTEM EQUIPMENT | R | DETAILED | PERFORMANCE | 2
291 | 6154-SA-MRQ-0323 | MR FOR F&G SYSTEM EQUIPMENT | R | DETAILED | PERFORMANCE | 3
292 | 6154-SA-TBE-0324 | TBE FOR F&G SYSTEM EQUIPMENT | A | DETAILED | PERFORMANCE | 4
293 | 6154-SA-MAN-0325 | DETAIL INSTALLATION DRAWING FOR FIR FIGHTING & SAFETY EQUIPMENT | A | BASIC | ENGINEERING | 5
294 | 6154-SA-CAL-0326 | HYDRULIC CALCULATION FOR WATER SPRAY SYSTEM | A | BASIC | ENGINEERING | 6
295 | 6154-SA-MAN-0327 | DETAIL INSTALLATION STANDARDDRAWING FIR WATER SPRAY NOZZLE | A | BASIC | ENGINEERING | 7
296 | 6154-SA-MTO-0328 | MTO FOR FIRE FIGHTING SYSTEM | R | DETAILED | PERFORMANCE | 8
297 | 6154-SA-MRQ-0329 | MR FOR FIRE FIGHTING SYSTEM | R | DETAILED | PERFORMANCE | 9
298 | 6154-SA-TBE-0330 | TBE FOR FIRE FIGHTING SYSTEM | A | DETAILED | PERFORMANCE | 10
SAFETY AND FIRE FIGHTING :
580 | 6154-SA-DIG-0656 | F&GSYSTEM BLOCK DIAGRAM | A | BASIC | ENGINEERING | 1
581 | 6154-SA-MTO-0657 | MTO FOR F&G SYSTEM EQUIPMENT | R | DETAILED | PERFORMANCE | 2
582 | 6154-SA-MRQ-0658 | MR FOR F&G SYSTEM EQUIPMENT | R | DETAILED | PERFORMANCE | 3
583 | 6154-SA-TBE-0659 | TBE FOR F&G SYSTEM EQUIPMENT | A | DETAILED | PERFORMANCE | 4
584 | 6154-SA-MAN-0660 | DETAIL INSTALLATION DRAWING FOR FIR FIGHTING & SAFETY EQUIPMENT | A | BASIC | ENGINEERING | 5
585 | 6154-SA-CAL-0661 | HYDRULIC CALCULATION FOR WATER SPRAY SYSTEM | A | BASIC | ENGINEERING | 6
586 | 6154-SA-MAN-0662 | DETAIL INSTALLATION STANDARDDRAWING FIR WATER SPRAY NOZZLE | A | BASIC | ENGINEERING | 7
587 | 6154-SA-MTO-0663 | MTO FOR FIRE FIGHTING SYSTEM | R | DETAILED | PERFORMANCE | 8
588 | 6154-SA-MRQ-0664 | MR FOR FIRE FIGHTING SYSTEM | R | DETAILED | PERFORMANCE | 9
589 | 6154-SA-TBE-0665 | TBE FOR FIRE FIGHTING SYSTEM | A | DETAILED | PERFORMANCE | 10
#REF!